## tasks
| HNC Games Graded Unit project |  | Group Name: Good island Games
| Item | Dates | Notes/comments | Team member assigned
PLANNING PHASE
1 | Pitch games and complie ideas | 2014-01-21 |  | All
2 | Start documenting planning stage | 2014-01-22 |  | All
3 | Decide on Game | 2014-01-28 |  | All
4 | Assign roles | 2014-01-28 |  | All
5 | Complete documenation for planning | 2014-01-29 |  | All
6 | Complete and compile all planning domuments | 04/01/2014 - 05/01/2014 | All team documents complete | Thomas
7 | Submit individual and team docs for planning phase | DEADLINE 06/02/14 | Deadline met √ | All
8 | DEVELOPMENT
9 | Game Design Document | 2014-02-18 |  | Craig
10 | GUI screen layouts | 2014-02-25 |  | Craig
11 | Create Flow charts | 2014-02-25 |  | Thomas
12 | Description of any/ all object, NPC | 2014-02-04 |  | Thomas with input from group
13 | Start pseudocode for all objects | 2014-03-12 |  | Alan
14 | Create background images | 2014-03-12 |  | Fionnlagh
15 | Start Create Sprites | 2013-03-19 |  | Fionnlagh (Thomas)
16 | Begin Coding | 2014-03-26 |  | Alan - Group to add input
17 | Create user interface | 2014-03-27 |  | Craig
18 | Start of College Holidays | 2014-04-07
19 | Back from College Holidays | 2014-04-15
20 | Find/ Create sound /music | 2014-04-15 |  | Fionnlagh
21 | Complete other menus | 2014-04-16 |  | Thomas
22 | Test complete game and complete test data | 2014-04-22 |  | All Group Lead by Thomas
23 | Submit game and team/indivdual docs | DEADLINE 01/05/14
EVALUATION
21 | peer evaluation | 2014-05-06
22 | Evaluation of game | 2014-05-14
23 | submit indvidual evaluation reports | 2012-05-15
24 | final project submissions including remediation | 2012-05-22

## resources
| HNC Games Graded Unit project |  |  | Group Name:
| Resource | number used | cost/month
materials | adobe flash cs5 | 5 | 12000
| adobe photoshop cs5 | 5 | 15500
| adobe illustrator cs5 | 5 | 12000
| pc | 5 | 3500
| word | 5 | 5000
| powerpoint | 1 | 2000
| internet usage | 5 | 900
| digital camera | 2 | 200
| Fireworks | 1 | 800
staff | project manager | 1 | 3000
| developer | 2 | 4000
| designer | 1.5 | 3500
| sound technician | 0.5 | 1000
monthly total estimated |  |  | 63400
317000
PROJECT TOTAL COST